## Rule Book Checklist
Section | Ref | Requirement | Design Decision to Lock | Cost Driver | Expected Completion | Open Question / Dependency | Flag | Status | Owner | Notes
UIUX Design | 0.1 | All Design and Prototype mentioned in the below requirements |  |  | 01-Jul-26 (Tendative) |  |  |  | Ashish
1. Users & Access Control | 1.1 | Replace shared super-admin login with individual staff accounts | Auth approach (own table / SSO), password policy | Auth + user-CRUD module | 2026-08-01 |  |  | Open
1. Users & Access Control | 1.2 | Super admin remains a distinct elevated role | Define super-admin-only powers | Role config |  |  |  | Open
1. Users & Access Control | 1.3 | Every billing/booking/review/payment action attributable to the acting user | Audit fields (who/when) on all transactional tables | Audit trail across all modules |  |  |  | Open
1. Users & Access Control | 1.4 | Each ritual completion attributable to a specific priest | Priest identity on completion record | Minor |  |  |  | Open
1. Users & Access Control | 1.5 | Define full role-permission matrix | Roles beyond staff/super admin: counter-billing, defaulted-puja reviewer, report viewer | RBAC granularity (costly to retrofit) |  | Matrix not yet supplied | F12 | Open
2. Puja Catalogue Restructuring | 2.1 | Model hierarchy Temple -> Sub-temple -> God -> Puja | Data model for the 4-level hierarchy | Schema + migration of existing god/puja rows |  |  |  | Open
2. Puja Catalogue Restructuring | 2.2 | Group repeating pujas into one master puja | Master-puja entity + linkage to instances | One-time de-dup migration of existing rows |  |  |  | Open
2. Puja Catalogue Restructuring | 2.3 | Editing master propagates to all linked listings | Propagation mechanism | Engine + tests |  | Depends on 2.5 |  | Open
2. Puja Catalogue Restructuring | 2.4 | Staff can edit a single puja instance under one god | Instance-level edit path | UI + logic |  | Depends on 2.5 |  | Open
2. Puja Catalogue Restructuring | 2.5 | Per-field: master-controlled vs instance-overridable | Does an instance edit permanently detach from master, or is it a per-field override that still inherits future master changes to non-overridden fields? | Determines the entire catalogue data model |  | BLOCKER | F1 | Open
3. Counter (Offline) Billing | 3.1 | Staff book pujas for walk-in queue devotees on the cloud admin app | Counter booking flow (reuse booking engine) | Counter UI | 2026-09-01 |  |  | Open
3. Counter (Offline) Billing | 3.2 | Print receipt via connected thermal printer | Browser->printer bridge (local agent / WebUSB / ESC-POS) | Hardware bridge - cost separately |  | Bridge method + printer model/protocol | F9 | Open
3. Counter (Offline) Billing | 3.3 | Counter runs on live internet (no disconnected mode) | Confirm no offline-outage billing required |  |  | Confirm scope |  | Open
3. Counter (Offline) Billing | 3.4 | Counter bookings feed revenue + incentive identically to app | Shared revenue/incentive path | Minor |  |  |  | Open
4. Booking Source Tracking | 4.1 | Record booking origin: counter-staff user / app / agent-code | Source field captured at every entry point | Minor, but cross-cutting | 2026-09-15 |  |  | Open
4. Booking Source Tracking | 4.2 | Record performing priest at completion | Performer field | Minor |  |  |  | Open
4. Booking Source Tracking | 4.3 | Source + performer are the authoritative incentive inputs |  |  |  | Feeds Section 5 |  | Open
5. Incentive Logic | 5.1 | Super admin defines incentive as % or absolute, with general default + per-puja override | Config schema: default rate + per-puja override + type flag | Incentive config + calc engine |  |  |  | Open
5. Incentive Logic | 5.2 | Incentives accrue to staff (bookings) and priests (completions) | Two accrual legs | Engine |  |  |  | Open
5. Incentive Logic | 5.3 | Accumulate totals per staff and per priest | Accrual ledger per person | Reporting view |  |  |  | Open
5. Incentive Logic | 5.4 | Define the % base | Gross puja price vs net-of-tax? Changes payout and auditor figures | Affects numbers everywhere |  | Confirm |  | Open
5. Incentive Logic | 5.5 | App-origin bookings have no staff | Who (if anyone) gets the staff-side incentive on app bookings? Does the priest still earn on app bookings? | Logic branch |  |  | F3 | Open
6. Attendance | 6.1 | Staff login = presence mark (login time captured) | Simple daily presence record | Minor | 2026-09-01 |  |  | Open
6. Attendance | 6.2 | Priest app login = presence mark | Same | Minor | 2026-09-15 |  |  | Open
6. Attendance | 6.3 | Priest presence valid only inside temple geofence | Geofencing on priest app | Geofencing module |  |  |  | Open
6. Attendance | 6.4 | Attendance is a record only - no effect on payout/incentive | Confirm and document the non-link | Avoids scope creep |  | Confirm |  | Open
6. Attendance | 6.5 | Geofence specifics | Radius; one-shot-at-login vs continuous; no-GPS/no-signal fallback; spoof tolerance | Edge-case handling |  |  | F5 | Open
7. Defaulted / Carried-Forward Puja Workflow | 7.1 | Priest may mark complete only on the scheduled day | Day-bound completion rule | Minor |  |  |  | Open
7. Defaulted / Carried-Forward Puja Workflow | 7.2 | Uncompleted puja carries forward, flagged defaulted | Defaulted state | State machine |  |  |  | Open
7. Defaulted / Carried-Forward Puja Workflow | 7.3 | Defaulted puja blocked until staff reviews + reassigns | Review->reassign gate in admin | Workflow |  |  |  | Open
7. Defaulted / Carried-Forward Puja Workflow | 7.4 | Review/reassign is admin-side; completion stays priest-app | Split of responsibility | Minor |  |  |  | Open
8. Agent-Code Booking & Deferred Offline Payment | 8.1 | Devotee app supports agent-code booking (existing) | Verify carried into new flow | Minor |  |  |  | Open
8. Agent-Code Booking & Deferred Offline Payment | 8.2 | Agent-code booking skips checkout payment (pay-on-visit) | Deferred-payment state | Logic |  |  |  | Open
8. Agent-Code Booking & Deferred Offline Payment | 8.3 | Generate QR for the unpaid booking | QR payload + uniqueness + expiry + anti-reuse | QR gen |  |  |  | Open
8. Agent-Code Booking & Deferred Offline Payment | 8.4 | Counter scans QR, completes offline payment | Scanner integration (HID keyboard-wedge vs bridge) | Scanner integration |  |  | F9 | Open
8. Agent-Code Booking & Deferred Offline Payment | 8.5 | Payment completion updates booking status + revenue | Status + revenue write | Minor |  |  |  | Open
8. Agent-Code Booking & Deferred Offline Payment | 8.6 | Lifecycle rules for unpaid agent-code pujas | Can a priest complete an unpaid puja? Revenue recognised at booking or at payment? No-show handling, and agent commission + priest incentive on a no-show? | Determines payment + revenue design |  | BLOCKER | F6 | Open
9. Reporting | 9.1 | Reports filterable by staff, priest, puja, date | Filter framework | Report engine |  |  |  | Open
9. Reporting | 9.2 | Daily / weekly / monthly, near-instant | Pre-aggregation vs on-demand | Performance/indexing |  |  |  | Open
9. Reporting | 9.3 | Report templates supplied by client | Templates are a prerequisite, not dev scope |  |  | Must be delivered & frozen before build | Dep | Open
9. Reporting | 9.4 | Monthly auditor report (GST/IT) = populate client template with source data | Field-mapping; specify any field the template derives | Template implementation |  | Template must be final & list every field/derivation | F7 | Open
10. Financial Module (Revenue & Expense) | 10.1 | Revenue = puja bookings (app + counter) + e-commerce product orders | Revenue aggregation | Aggregation logic |  |  |  | Open
10. Financial Module (Revenue & Expense) | 10.2 | Expense = incentive payouts only (staff + priest) - not base salary, not attendance-derived | Confirm base salary lives outside the system | Avoids payroll build |  | Confirm |  | Open
10. Financial Module (Revenue & Expense) | 10.3 | No double-entry / general ledger in scope | Explicit exclusion |  |  |  |  | Open
10. Financial Module (Revenue & Expense) | 10.4 | Refunds / cancellations / product returns | Scope in or out? They reverse revenue + incentives if in | Reversal logic |  | Must be stated explicitly | F13 | Open
11. WhatsApp Business API (Conditional) | 11.1 | If client provides WA Business API: alerts on booking + on completion | Trigger points + message templates | Conditional integration - cost separately |  | Client provisions API; Meta-approved templates | Dep | Open
12. Hardware Bridge (cross-cuts 3 & 8) | 12.1 | Thermal printer + QR scanner driven from a web app | One local-bridge strategy for both | Local agent dev + per-site setup/support |  | A web app cannot reliably drive local hardware without a bridge | F9 | Open

## Open Decisions
Priority | Flag | Issue | Ref
P1 - BLOCKER | F1 | Master vs instance puja edit: detach permanently, or per-field override with inheritance? | 2.5
P1 - BLOCKER | F6 | Deferred agent-code payment lifecycle: completion-before-payment, revenue timing, no-show + commission/incentive. | 8.6
P2 | F3 | Staff incentive on app-origin bookings (and does priest still earn). | 5.5
P2 | F5 | Geofence rules (radius, continuous vs one-shot, no-signal/spoof). | 6.5
P2 | F7 | Auditor template must be final and field-complete. | 9.4
P2 | F9 | Browser-to-hardware bridge method for printer + scanner. | 3.2 / 8.4 / 12.1
P2 | F12 | Full role-permission matrix. | 1.5
P2 | F13 | Refunds/cancellations explicitly scoped in or out. | 10.4
P2 | - | Incentive % base: gross vs net-of-tax. | 5.4
P2 | - | Confirm base salary is recorded entirely outside the system. | 10.2